## Sheet1
Week - 1
ACTIVITY | WHAT IT MEANS | WHY THIS WEEK
Finalise message tree & copy | Lock the IVR script, yes/no/non-response flows. | The customer journey must be clear before testing.
Onboard WhatsApp approval, voice fallback | Define backup/alternate confirmation paths for missed or failed calls. | Channel logic must be ready before customers enter the pilot.
Build risk score V0 | Create a simple first version to identify likely fake/high-risk COD orders. | Needed to target the pilot where the benefit is highest.
Define success & guardrail metrics | Set impact metrics plus checks for cancellations, complaints and friction. | Metrics must be fixed before launch to measure the pilot objectively.
Set hold window & QA | Decide how long to wait for confirmation and test all key journeys. | Prevents genuine orders being wrongly blocked or delayed.
Week - 2
ACTIVITY | WHAT IT MEANS | WHY THIS WEEK
Launch on top risk decile | Test IVR on the highest-risk 10% of COD orders. | Limits exposure while maximising learning.
Run a matched control group | Keep a similar group without IVR for comparison. | Shows incremental impact rather than simple before/after change.
Track response & confirm rates | Measure answered, yes, no, missed and failed calls. | These are the earliest signals that the product works.
Measure prepaid conversion | Track whether confirmation nudges customers toward prepaid, where applicable. | Captures additional value beyond fake-order prevention.
Watch induced cancellations | Separate intentional rejection from unwanted cancellation caused by IVR friction. | Critical guardrail before expanding the experience.
Week - 3
ACTIVITY | WHAT IT MEANS | WHY THIS WEEK
Improve copy, timing & channel order | Optimise what is said, when the call happens and the contact sequence. | Now there is real customer behaviour to learn from.
Widen the risk band | Extend IVR beyond the top 10% to the next high-risk segment. | Tests whether results hold beyond the highest-risk orders.
Gate expansion on leading indicators | Expand only if response quality and guardrails stay healthy. | Makes rollout evidence-led, not calendar-led.
Optimise retry cadence | Tune number and timing of follow-up attempts. | Week 2 shows where missed calls can be recovered without annoyance.
Add a second language | Introduce another high-reach language while keeping the core journey unchanged. | Base experience should be stable before localisation.
Week - 4
ACTIVITY | WHAT IT MEANS | WHY THIS WEEK
First readout against control | Compare IVR vs control on impact and guardrails. | Provides the evidence needed for a scale decision.
Split invalid from low-intent impact | Distinguish fake orders from genuine customers who simply did not respond. | Prevents the solution from mistaking non-response for fraud.
Confirm rider earnings unmoved | Check that reduced fake orders do not create unintended rider impact. | Ensures the fix works for the wider delivery ecosystem.
Scale to full high-risk band | Roll out across the validated high-risk population. | Scale follows evidence rather than assumption.
Decide: scale, tune or kill | Continue, refine or stop based on impact, CX and economics. | Creates a clear product decision instead of scaling by default.